## Executive Summary
Ship Sticks Data Analyst Agent MVP
Project Roadmap & Delivery Plan
Project Overview
Duration: | 30 Days Development + 30 Days Support
Total Effort: | 298 Hours
Investment:
Phases: | 8 Major Phases
Key Deliverables: | 13 Client-Facing Deliverables
Team Structure: | Cross-Functional AI Development Team
Project Phases
Phase 1-2: | Foundation & Data Integration | Week 1-2 | Database connectivity, security setup
Phase 3-4: | AI Core Development | Week 2-3 | Text-to-SQL engine, learning system
Phase 5: | User Interface | Week 3-4 | Executive dashboard, responsive design
Phase 6: | Quality Assurance | Week 4 | Testing, optimization, UAT
Phase 7: | Deployment & Training | Week 4-5 | Go-live, documentation, training
Phase 8: | Post-Launch Support | Week 5-8 | Monitoring, refinements, optimization
What Ship Sticks Receives
✓ Production-Ready AI Data Analyst Agent
✓ Executive Intelligence Dashboard
✓ BigQuery Integration with Real-Time Data Access
✓ Intelligent Learning System with Feedback Loop
✓ Comprehensive User & Technical Documentation
✓ Training for Ship Sticks Team
✓ 30 Days of Post-Launch Support & Optimization
✓ Weekly Status Reports During Support Period
Our Commitment to Quality
No Shortcuts: | Proper development methodology with testing at every phase
Proven Technology: | Next.js 16, LangChain, LangGraph - enterprise-grade frameworks
Security First: | Data encryption, access controls, security audits
Knowledge Transfer: | Complete documentation and hands-on training
Continuous Support: | Not just delivery - ongoing optimization and support
Clear Accountability: | Defined acceptance criteria for every deliverable
Next Steps
1. Review and approve Statement of Work
2. Sign SOW and submit 50% deposit
3. Schedule project kickoff meeting
4. Provide BigQuery access credentials
5. Identify key stakeholders for requirements session
6. Week 1: Project begins!

## Project Roadmap
Ship Sticks Data Analyst Agent - Project Roadmap
Generated: November 12, 2025
Timeline: 30 Days Development + 30 Days Post-Launch Support
Phase | Week | Duration | Key Activities | Client Deliverables | Internal Work | Dependencies | Status
Phase 1: Discovery & Planning | Week 1 | 3 days | Requirements gathering, data access setup, technical architecture planning | Project kickoff meeting, data access confirmation | Environment setup, BigQuery connection testing, architecture documentation | Client provides BigQuery credentials | Foundation
Phase 2: Data Integration | Week 1-2 | 5 days | BigQuery integration, data schema mapping, query optimization | Data connectivity demo, schema documentation | ETL pipeline setup, data validation scripts, security configurations | Phase 1 complete | Foundation
Phase 3: AI Agent Core Development | Week 2-3 | 7 days | Text-to-SQL engine development, natural language processing, query generation logic | Working agent prototype, sample query demonstrations | LangChain integration, LangGraph workflow design, prompt engineering | Phase 2 complete | Core Build
Phase 4: Intelligence Layer | Week 3 | 4 days | Reinforcement learning system, feedback tracking, response optimization | Learning system demonstration, feedback mechanism preview | Feedback loop implementation, response quality scoring, improvement algorithms | Phase 3 complete | Core Build
Phase 5: User Interface Development | Week 3-4 | 5 days | Dashboard design, executive interface, data visualization components | Live dashboard preview, UI/UX walkthrough | Next.js 16 frontend, responsive design, chart libraries integration | Phase 3 in progress | User Experience
Phase 6: Testing & Quality Assurance | Week 4 | 4 days | End-to-end testing, performance optimization, security review | UAT session, testing documentation | Automated testing, load testing, security audit, bug fixes | Phases 3, 4, 5 complete | Quality
Phase 7: Deployment & Training | Week 4-5 | 2 days | Production deployment, user training, documentation handover | Production system live, user guide, training session, technical docs | Production environment setup, monitoring configuration, backup procedures | Phase 6 complete, client UAT approval | Launch
Phase 8: Post-Launch Support | Week 5-8 | 30 days | Performance monitoring, issue resolution, optimization, refinements | Weekly status reports, optimization recommendations, issue resolutions | Bug monitoring, performance tracking, user feedback collection | Phase 7 complete | Support

## Detailed Tasks
Detailed Task Breakdown
Phase | Task ID | Task Name | Description | Effort (hrs) | Owner | Type
Phase 1 | T1.1 | Kickoff Meeting | Initial meeting with stakeholders to align on objectives | 2 | Project Manager | Planning
Phase 1 | T1.2 | Requirements Documentation | Document functional and technical requirements | 4 | Solutions Architect | Planning
Phase 1 | T1.3 | Data Access Setup | Obtain and validate BigQuery credentials | 3 | Data Engineer | Technical
Phase 1 | T1.4 | Architecture Design | Design system architecture and data flow | 6 | Solutions Architect | Technical
Phase 2 | T2.1 | BigQuery Connection | Establish secure connection to BigQuery | 4 | Data Engineer | Development
Phase 2 | T2.2 | Schema Mapping | Map database schema to application requirements | 6 | Data Engineer | Development
Phase 2 | T2.3 | Data Validation | Validate data quality and completeness | 5 | Data Engineer | Testing
Phase 2 | T2.4 | Query Optimization | Optimize query performance for large datasets | 8 | Data Engineer | Development
Phase 2 | T2.5 | Security Configuration | Implement security protocols and access controls | 5 | Data Engineer | Technical
Phase 3 | T3.1 | LangChain Setup | Configure LangChain framework | 6 | AI Developer | Development
Phase 3 | T3.2 | LangGraph Workflow | Design and implement LangGraph agent workflow | 12 | AI Developer | Development
Phase 3 | T3.3 | Text-to-SQL Engine | Build natural language to SQL translation engine | 16 | AI Developer | Development
Phase 3 | T3.4 | Prompt Engineering | Develop and optimize prompts for accuracy | 10 | AI Developer | Development
Phase 3 | T3.5 | Context Management | Implement conversation context tracking | 8 | AI Developer | Development
Phase 4 | T4.1 | Feedback System Design | Design user feedback collection mechanism | 4 | AI Developer | Development
Phase 4 | T4.2 | Learning Algorithm | Implement reinforcement learning algorithm | 10 | AI Developer | Development
Phase 4 | T4.3 | Response Scoring | Build response quality scoring system | 6 | AI Developer | Development
Phase 4 | T4.4 | Model Improvement Loop | Create continuous improvement pipeline | 8 | AI Developer | Development
Phase 5 | T5.1 | UI/UX Design | Design executive-friendly interface mockups | 8 | Frontend Developer | Design
Phase 5 | T5.2 | Next.js Setup | Initialize Next.js 16 application | 4 | Frontend Developer | Development
Phase 5 | T5.3 | Dashboard Development | Build interactive dashboard components | 12 | Frontend Developer | Development
Phase 5 | T5.4 | Data Visualization | Implement charts and data visualization | 10 | Frontend Developer | Development
Phase 5 | T5.5 | Chat Interface | Build conversational interface for agent | 8 | Frontend Developer | Development
Phase 5 | T5.6 | Responsive Design | Ensure mobile and tablet compatibility | 6 | Frontend Developer | Development
Phase 6 | T6.1 | Unit Testing | Write and execute unit tests for all components | 8 | QA Engineer | Testing
Phase 6 | T6.2 | Integration Testing | Test end-to-end system integration | 6 | QA Engineer | Testing
Phase 6 | T6.3 | Performance Testing | Load testing and performance optimization | 8 | QA Engineer | Testing
Phase 6 | T6.4 | Security Testing | Security audit and penetration testing | 6 | QA Engineer | Testing
Phase 6 | T6.5 | UAT Preparation | Prepare UAT environment and test cases | 4 | QA Engineer | Testing
Phase 6 | T6.6 | Bug Fixes | Resolve identified issues and defects | 8 | Development Team | Development
Phase 7 | T7.1 | Production Setup | Configure production environment | 6 | DevOps | Technical
Phase 7 | T7.2 | Deployment | Deploy application to production | 4 | DevOps | Technical
Phase 7 | T7.3 | User Documentation | Create user guides and best practices | 8 | Technical Writer | Documentation
Phase 7 | T7.4 | Technical Documentation | Document architecture and maintenance procedures | 6 | Solutions Architect | Documentation
Phase 7 | T7.5 | Training Session | Conduct user training for Ship Sticks team | 3 | Project Manager | Training
Phase 8 | T8.1 | Monitoring Setup | Configure performance and error monitoring | 4 | DevOps | Technical
Phase 8 | T8.2 | Issue Triage | Monitor and triage reported issues | 20 | Support Team | Support
Phase 8 | T8.3 | Performance Optimization | Optimize based on real-world usage | 12 | Development Team | Development
Phase 8 | T8.4 | User Feedback Review | Collect and analyze user feedback | 8 | Product Manager | Support
Phase 8 | T8.5 | Refinements | Implement minor improvements and fixes | 16 | Development Team | Development
|  |  | Total Effort: | 298

## Client Deliverables
Client Deliverables & Milestones
What Ship Sticks Will Receive
Milestone | Timeline | Deliverable | Format | Acceptance Criteria
Project Kickoff | Week 1, Day 1 | Project Kickoff Meeting | Virtual Meeting | Stakeholders aligned on objectives, timeline, and success criteria
Data Access Confirmed | Week 1, Day 3 | BigQuery Access Validation | Technical Demo | Successful connection to BigQuery, ability to query Ship Sticks data
Data Integration Complete | End of Week 2 | Data Schema Documentation | PDF Document | Complete documentation of data structure, relationships, and query patterns
Agent Prototype | Week 3, Day 2 | Working AI Agent Demo | Live Demo | Agent successfully answers 10+ sample business questions with accurate results
Learning System Demo | Week 3, Day 5 | Feedback Mechanism Preview | Live Demo | Demonstration of feedback capture and learning loop functionality
Dashboard Preview | End of Week 3 | Executive Dashboard Walkthrough | Live Demo | Interactive dashboard showing key metrics and visualizations
UAT Session | Week 4, Day 3 | User Acceptance Testing | Testing Session | Ship Sticks team validates functionality against requirements
Production System | End of Week 4 | Live Application | Web Application | Fully functional system accessible via browser with all features operational
User Guide | Week 5, Day 1 | User Documentation | PDF + Online | Comprehensive guide on using the Data Analyst Agent effectively
Technical Docs | Week 5, Day 1 | Technical Documentation | PDF Document | Architecture documentation, maintenance procedures, API references
Training Complete | Week 5, Day 2 | User Training Session | Virtual Training | Ship Sticks team trained on system usage and best practices
Weekly Status Reports | Weeks 5-8 | Post-Launch Reports | Email/PDF | Weekly summary of usage, issues resolved, and optimization recommendations
Support & Optimization | Weeks 5-8 | Ongoing Support | Email/Video | Rapid issue resolution, performance monitoring, system refinements

## Risk & Mitigation
Risk Management & Mitigation Strategies
Proactive Risk Planning to Ensure Project Success
Risk Category | Potential Risk | Impact | Probability | Mitigation Strategy | Contingency Plan
Data Access | Delays in obtaining BigQuery credentials | High | Medium | Request credentials in kickoff meeting; provide detailed access requirements list | Use sample/mock data for initial development; parallel track credential request
Data Quality | Incomplete or inconsistent data in BigQuery | Medium | Medium | Conduct early data quality assessment; document data gaps in schema mapping | Build data validation layer; implement graceful error handling
Technical | Complex queries causing performance issues | Medium | Low | Implement query optimization from start; use BigQuery best practices | Add query caching layer; implement async query processing
AI Accuracy | Agent generates incorrect SQL queries | High | Medium | Extensive prompt engineering; build comprehensive test suite with edge cases | Implement query validation layer; show generated SQL for user review
Scope | Client requests additional features during development | Medium | High | Clear SOW with defined scope; change request process documented | Parking lot for future enhancements; Phase 2 development option
Integration | Compatibility issues with existing Ship Sticks systems | Low | Low | Standalone application design; standard web technologies | API-first architecture allows easy integration later
Adoption | Users struggle with natural language queries | Medium | Medium | Provide query templates and examples; comprehensive training | Build guided query builder; suggested questions feature
Timeline | Development delays due to technical complexity | Medium | Low | Experienced team; proven technology stack; buffer time in estimates | Prioritize core features; defer nice-to-have items to post-launch
Security | Data security or access control concerns | High | Low | Follow security best practices; encryption in transit and at rest | Security audit before launch; implement role-based access control
User Feedback | Learning system receives insufficient feedback | Low | Medium | Design intuitive feedback UI; encourage feedback in training | Implement implicit feedback signals; periodic quality reviews
Infrastructure | Hosting or performance issues at scale | Medium | Low | Use proven cloud infrastructure; implement monitoring from day one | Auto-scaling configuration; performance optimization sprint if needed
Knowledge Transfer | Ship Sticks team not ready to maintain system | Low | Low | Comprehensive documentation; hands-on training sessions | Extended support period; recorded training videos available

## Success Metrics
Project Success Metrics
How We Measure Success
Category | Success Metric | Target | Measurement Method
Technical | Agent Query Accuracy | 90%+ correct SQL generation | Test suite of 100+ sample questions with known correct answers
Technical | Response Time | < 3 seconds for standard queries | Performance monitoring on production queries
Technical | System Uptime | 99%+ availability | Infrastructure monitoring and uptime tracking
Technical | Data Refresh | Real-time data access | Query timestamps match BigQuery current state
User Experience | User Satisfaction | 4.0+ out of 5.0 rating | Post-training survey and ongoing feedback collection
User Experience | Ease of Use | 80%+ users successful on first try | Track successful query completion without assistance
User Experience | Training Effectiveness | 90%+ comprehension | Training assessment and follow-up questions
Business Value | Executive Adoption | 5+ regular executive users | User analytics and login frequency tracking
Business Value | Query Volume | 50+ queries per week | Usage analytics and query logging
Business Value | Insight Generation | 10+ actionable insights per month | User feedback on valuable discoveries
Business Value | Time Savings | 5+ hours saved per week | User survey on time saved vs manual analysis
Learning System | Feedback Rate | 30%+ queries receive feedback | Feedback collection metrics
Learning System | Improvement Over Time | Accuracy improves 5%+ monthly | Track accuracy trends over time
Learning System | User Corrections | < 10% queries need correction | Track user modifications to agent responses
Project Delivery | On-Time Delivery | 100% phases delivered on schedule | Project timeline tracking
Project Delivery | Budget Adherence | 100% within agreed budget | Financial tracking vs SOW
Project Delivery | Scope Completion | 100% SOW deliverables met | Deliverable checklist completion
Project Delivery | Client Approval | UAT sign-off within 5 days | Acceptance documentation
Post-Launch | Critical Issues | 0 critical bugs post-launch | Issue tracking and severity classification
Post-Launch | Support Response Time | < 4 hours for critical issues | Support ticket response time tracking
Post-Launch | Documentation Quality | 90%+ users find docs helpful | Documentation feedback survey